## Agile Project Plan
BLOOD BANK AGILE PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| O for Owesome's Blood Bank | Mikkie | 2022-05-30 | 2022-06-23 |  | 44% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  |  | 2022-05-30 | 2022-06-07 | 9 | COMPLETE
| Setup |  | Mikkie |  | 2022-05-30 | 2022-05-30 | 1 | COMPLETE
| SWOT & Requirements |  | Delear |  | 2022-05-31 | 2022-06-07 | 8 | COMPLETE
| UML Diagrams |  | Sese |  | 2022-05-31 | 2022-06-07 | 8 | COMPLETE
| Sprint 2 |  |  |  | 2022-06-08 | 2022-06-15 | 8 | IN PROGRESS
| Registration, Stock management |  | Sese |  | 2022-06-08 | 2022-06-15 | 8 | IN PROGRESS
| Booking Appointments |  | Delear |  | 2022-06-08 | 2022-06-15 | 8 | IN PROGRESS
| Users, Permissions & Login |  | Mikkie |  | 2022-06-08 | 2022-06-15 | 8 | IN PROGRESS
| Sprint 3 |  |  |  | 2022-06-13 | 2022-06-19 | 7 | NOT STARTED
| Bug checking |  |  |  | 2022-06-13 | 2022-06-19 | 7 | NOT STARTED
| Testing |  |  |  | 2022-06-13 | 2022-06-19 | 7 | NOT STARTED
| More Testing |  |  |  | 2022-06-13 | 2022-06-19 | 7 | NOT STARTED
| Sprint 4 |  |  |  | 2022-06-20 | 2022-06-23 | 4 | NOT STARTED
| Report |  |  |  | 2022-06-20 | 2022-06-23 | 4 | NOT STARTED
| Powerpoint |  |  |  | 2022-06-20 | 2022-06-23 | 4 | NOT STARTED
| Polish Application |  |  |  | 2022-06-20 | 2022-06-23 | 4 | NOT STARTED